## Agile Product Backlog
SPRINT BACKLOG
SPRINT # | STATUS | User Story | Tasks | ASSIGNED TO | STORY POINTS | START DATE | Date completed | Definition of Done | Velocity 1 | Velocity 2 | Extra work done sprint 1
Sprint 1 |  |  |  |  | 140 | [5 empty] | 39
| In Progress | As a member of staff, I want to be able to create questionnaires via the system, so that I don’t need to use external systems | Design and create database (questionnaire: title, questions, answers): - Create ER diagram - Normalise - Create database - Add data | Craig and Wei | 55 | 26/01/2021 |  | -The created questionaire should be saved in a database -The database should at least satisfy 3NF | This section is for the drop-down list
| In Progress |  | Design and create website: - Desgin pages (website template, create questionnaire page) - Create pages (website template, create questionnaire page) | Elliot, Alban, Zihan and Tianpeng |  | 26/01/2021 |  | -The website should look professional and the design should be approved by the stake holders -The website should have university branding -The text design should satifsy WCAG 2.0 AA | Yes | High | Complete
| In Progress |  | Java script and php, questionaire logic: - Connect to the database - Create a new questionnaire - Add questions | (Jonas & Tony) Elliot, Alban, Zihan and Tianpeng |  | 27/01/2021 |  | -The website has an ability to create and store a questionaire -The creator should be easy and intuitive to use approved by the stake holders -The website should be able to send the questionaire to be stored in the database
| Complete | As a user of the program, I want to be able to login so that I can access my information easily | Design and add to database (login: username, real name, password, role, access rights): - Add to ER diagram - Normalise - Add to database - Add data | Craig and Wei | 55 | 26/01/2021 | 27/01//2021 | -The database should at least satisfy 3NF -The database should be able to store users and all needed data -Data about the users are name, role and permissions at the least
| Complete |  | Design and create pages: - login page | Elliot, Alban, Zihan and Tianpeng |  | 26/01/2021 | 27/01//2021 | -The website should look professional and the design should be approved by the stake holders -The website should have university branding -The text design should satifsy WCAG 2.0 AA
| Complete |  | Java script and php, questionaire logic: - Check login details against stored data, return appropriate result | (Jonas & Tony) Elliot and Alban |  | 27/01/2021 | 27/01/2021 | -The website should be locked and redirect to login page If the user is not looged in -The user should be able to login and access info saved on the site -When the user is logged in they should be able to see their name and role
| Complete | As a member of staff, I need to ensure that participants have agreed to our privacy policy before they start the questionnaire, so the participant understand how are were going to use their data and that we don't violate the Data protection act and GDPR | Research, design and create page: - Collect privacy policy - design page - create page | Elliot, Alban, Zihan and Tianpeng | 2 | 27/01/2021 | 27/01/2021 | -The website should post our privacy policy before participants can access any questionaires -The participant have to accept it before they can go futher into the website
| Not Started |  | Add to database: - user accepted/rejected | Craig and Wei |  |  |  | - Users can accespt or reject terms and conditions - response is correctly stored in the database
| Not Started |  | Add accept/reject functionality | (Jonas & Tony) Elliot and Alban |  |  |  | - When a user has accepted, they will be able to continue as a participant - When a user rejects terms and conditions, they are removed from that experiment
| Complete | As a member of staff, I need to ensure that participants have agreed to the UoD Ethics before they start the questionnaire, so that we don't violate the user privacy | Research, design and create page: - Collect privacy policy - design page - create page | Elliot, Alban, Zihan and Tianpeng | 2 | 27/01/2021 | 27/01/2021 | -The website should post our UoD Ethics before participants can access any questionaires -The participant have to accept it before they can go futher into the website
| Not Started |  | Add to database: - user accepted/rejected | Craig and Wei |  |  |  | - Users can accespt or reject terms and conditions - response is correctly stored in the database
| Not Started |  | Add accept/reject functionality | (Jonas & Tony) Elliot and Alban |  |  |  | - When a user has accepted, they will be able to continue as a participant - When a user rejects terms and conditions, they are removed from that experiment
| Complete | As a participant. I want the ability to check the T&Cs before participating in the questionnaire so that I know information about myself is being used correctly | Research, design and create page: - Collect privacy policy - design page - create page | Elliot, Alban, Zihan and Tianpeng | 3 | 27/01/2021 | 27/01/2021 | -The website should post our T&Cs before participants can access any questionaires -The participant have to accept it before they can go futher into the website
| Not Started |  | Add to database: - user accepted/rejected | Craig and Wei |  |  |  | - Users can accespt or reject terms and conditions - response is correctly stored in the database
| Not Started |  | Add accept/reject functionality | (Jonas & Tony) Elliot and Alban |  |  |  | - When a user has accepted, they will be able to continue as a participant - When a user rejects terms and conditions, they are removed from that experiment
| Complete | As a lab manager, I want to be able to create accounts so that new people can access the system | Create a stored procedure for adding a new user to the database | Craig and Wei | 13 |  | 28/01/2021 | - A stored procedure is available that creates a new user entry in the database with all the relevant information
| Complete |  | Design and create page: - lab manager, create new user | Elliot, Alban and Tianpeng |  |  | 28/01/2021 | -The website should look professional and the design should be approved by the stake holders -The website should have university branding -The text design should satifsy WCAG 2.0 AA -There should be a form where lab managers can add new users and enter all their data | No | Medium | In Progress
| Complete |  | Java script and php, questionaire logic: link database and html login functionality | (Jonas & Tony) Elliot and Alban |  |  | 28/01/2021 | -When a lab manager adds a new user they are created in the database correctly
| Not Started | As a member of staff, I want questionnaires to have options for text answers, so that I can gauge responses accurately | Design and add to database: - store text answers, user ID | Craig and Wei | 5 |  |  | -The database should at least satisfy 3NF -The database should be able to store users and all needed data -The database should be able to store Text type answers
| Not Started |  | Design and create: - text input option when creating a questionnaire - participant questionnaire answer page | Elliot, Alban and Tianpeng |  |  |  | -The website should look professional and the design should be approved by the stake holders -The website should have university branding -The text design should satifsy WCAG 2.0 AA -in the create questionaire sthere should be an qption to make text type questions
| Not Started |  | Java script and php, questionaire logic: send questionnaire results to be stored in the database | (Jonas & Tony) Elliot and Alban |  |  |  | It should be possible for the text type question to be saved in the database
| Not Started | As a member of staff, I want questionnaires to have options for multiple choice answers, so that I can gauge responses accurately | Design and add to database: - store multiple choice answers, user ID | Craig and Wei | 5 |  |  | -The database should at least satisfy 3NF -The database should be able to store users and all needed data -The database should be able to store multiple choice answers
| Not Started |  | Design and create: - multiple choice input option when creating a questionnaire | Elliot, Alban and Tianpeng |  |  |  | -The website should look professional and the design should be approved by the stake holders -The website should have university branding -The text design should satifsy WCAG 2.0 AA -In the create Questionaire page there should be a multiple choice ype question
| Not Started |  | Java script and php, questionaire logic: send questionnaire results to be stored in the database | (Jonas & Tony) Elliot and Alban |  |  |  | -It should be possible for the multiple choice question to be saved in the database
extra work done
| Complete | As a user of the program, I want access to a dashboard so that I can see and access the functionalities of the program I have access to | - users are able to access their dashboard | Craig | 13 |  | 28/01/2021
| Complete | As a user of the program, I want to be able to see what "role" I've logged into so that I know I am accessing the relevant information | - the user's role is visable on the dashboard | Craig | 8 |  | 28/01/2021
| Complete | As a lab manager, I want to be able to reset the passwords of accounts so that users who have forgotten their passwords can gain access | - lab managers are able to select a user and replace the corresponding password value with the default value "password" | Craig | 13 |  | 28/01/2021
| Complete | As a lab manager, I want to be able to give other accounts different roles so that people can access what they need to | - lab managers can select accounts and select a new role - relevant data is updated in the database | Craig | 5 |  | 28/01/2021
Questionnaire | Complete | As a member of staff, I NEED to be able to export results from the questionnaires to CSV files, so that I can impot them into our data analysis software | -All answers to the questionaires should be able to be exported to a CSV file. | Craig | 8 |  |  |  |  | Low | Not Started
SPRINT # | STATUS | User Story | Tasks | ASSIGNED TO | STORY POINTS | START DATE | Date completed | Definition of Done
Sprint 2 |  |  |  |  | 134
| In Progress | As a member of staff, I want to be able to create questionnaires via the system, so that I don’t need to use external systems | Design and create database (questionnaire: title, questions, answers): - Create ER diagram - Normalise - Create database - Add data Design and create website: - Desgin pages (website template, create questionnaire page) - Create pages (website template, create questionnaire page) Java script and php, questionaire logic: - Connect to the database - Create a new questionnaire - Add questions | Elliot, Alban (Jonas, Tony) | 55 | 26/01/2021 |  | -The website should look professional and the design should be approved by the stake holders -The website should have university branding -The text design should satifsy WCAG 2.0 AA -The created questionaire should be saved in a database -The database should at least satisfy 3NF -The website has an ability to create and store a questionaire -The creator should be easy and intuitive to use approved by the stake holders -The website should be able to send the questionaire to be stored in the database
| In Progress | As a member of staff, I want questionnaires to have options for text answers, so that I can gauge responses accurately | - Select what answer type a question should have when creating a questionnaire (text) | Elliot, Alban (Jonas, Tony) | 8 | 26/01/2021 |  | - Users are able to select 'text answers' when creating a new quesiton
| In Progress |  | - store appropriate information in the database (question answer type and text answer) | Elliot, Alban (Jonas, Tony) |  | 26/01/2021 |  | The following muse be stored in the database after saving a questionnaire with quesiton(s) containing text based answers: - the question - type of answer - null field for the answer
| In Progress | As a member of staff, I want questionnaires to have options for multiple choice answers, so that I can gauge responses accurately | - Select what answer type a question should have when creating a questionnaire (multiple choice) | Elliot, Alban (Jonas, Tony) | 8 |  |  | - Users are able to select 'multiple choice' when creating a new quesiton
| In Progress |  | - store appropriate information in the database (question answer type and multiple choice answer) | Elliot, Alban (Jonas, Tony) |  |  |  | The following muse be stored in the database after saving a questionnaire with quesiton(s) containing multiple choice answers: - the question - type of answer - null field for the answer
| In Progress | As a member of staff, I want questionnaires to have options for Likert Scored answers, so that I can gauge responses accurately | - Select what answer type a question should have when creating a questionnaire (Likert Scored) | Elliot, Alban (Jonas, Tony) | 2 |  |  | - Users are able to select 'Likert Scored answers' when creating a new quesiton
| In Progress |  | - store appropriate information in the database (question answer type and Likert Scored answer) | Elliot, Alban (Jonas, Tony) |  |  |  | The following muse be stored in the database after saving a questionnaire with quesiton(s) containing Likert Scored based answers: - the question - type of answer - null field for the answer
| Complete | As a participant, I can answer questionnaires that I have access to, so that I can participate in experiments | - Retrieve questions from the database | Craig, Zihan | 5 | 2021-01-02 | 2021-01-02 | - All question data from the appropriate questionnaire is retrieved from the database: questions, answer type
| Complete |  | - generate questionnarie and display | Craig, Zihan |  | 2021-01-02 | 2021-01-02 | - Questions are displayed in the correct format, participants have the ability to answer appropriately (text fields for text based answers, multiple choice radio buttons etc.)
| Complete |  | - store answers in the database once all questions have been answered | Craig, Zihan |  | 2021-01-02 | 2021-01-02 | - Submit button stores answers, participant ID and questionnaire ID in the database
| Complete |  | - mark questionnaire as 'completed' by the appropriate participant | Craig, Zihan |  | 2021-01-02 | 2021-01-02 | - After a questionnaire is completed by a particpant, they should no longer be able to take that questionnaire
| In Progress | As a member of staff, I want the system to look professional (as deemed by the clients), so that the data it consistent | - Add template to all site pages | Tony | 5 | 2021-01-02 |  | - Headder, font, university branding should be present and correct on every site page
| In Progress |  | - Change the colour of hyperlinks | Tony |  | 2021-01-02 |  | - Hyperlinks in the headder should apear white
| In Progress | As a member of staff, I want to be able to delete questionnaires I created, so that they can be managed better | - Remove all data from the database associated with the questionnaire being deleted | Wei, Tianpeng | 5 | 2021-01-02 |  | - members of staff can deleted existing questionnaires
| Not Started | As a member of staff, I want to be able to edit questionnaires I created, so that they can be managed better | - Open selected questionnaire in editor |  | 8 |  |  | - members of staff can edit existing questionnaires
| Not Started |  | - Replace/add any new entries in the questionnaire to the database when 'save' is clicked
| Complete | As a member of staff, I want to be able to see simple charts visualising the data, so that I can see roughly how things are looking | - Select questionnaire to be visualised, retrieve data from the database | Craig, Zihan | 21 | 2021-01-02 | 2021-02-02 | - Charts can be created from existing data
| Complete |  | - display generated graph from stored data associated with that questionnaire | Craig, Zihan |  | 2021-01-02 | 2021-02-02 | - Charts can be viewed by members of staff uppon request by selecting a questionnaire that has been completed by at least one participant
| Complete | As a participant, I want the questionnaires to be easy to use, so that I can complete them correctly and efficiently | - Buttons/input fields are labled correctly | Craig, Zihan | 5 | 2021-01-02 | 2021-01-02 | - all page functionalities (buttons and input fields) are labled appropriately
| Complete |  | - Design makes using the program intuitive and easy to follow | Craig, Zihan |  | 2021-01-02 | 2021-01-02 | - Web pages are intuitive, easy to navigate
| Not Started | As a PR, I want to be able to select what access rights different co-researchers have to add,edit and delete questionnaires, view results and review video footage. So that I can control who has access to what information | - When assigning a new co-researcher, access rights options should be available |  | 5 |  |  | - When adding a co-researcher, options for what permissions they have should be available - they can select what questionnaires they are allowed access to and what actions they can perform (view results, edit, delete etc.)
| Not Started |  | - Co-researcher's permissions should be editable |  |  |  |  | - PR's should also have an option to add/remove permissions (either from the same page, or a link to editing permissions should be on the same page as adding co-researchers)
| Not Started | As a member of staff, I need to ensure that participants have agreed to our privacy policy before they start the questionnaire, so the participant understand how are were going to use their data and that we don't violate the Data protection act and GDPR | - Revoke access to the questionnaire if the policy is rejected |  | 3 |  |  | - Before a user starts a questionnaire, they need to agree to a privacy policy. If the user rejects the privacy policy agreement, they cannot continue.
| Not Started |  | - option to change response if the questionnaire has not yet been completed |  |  |  |  | - Participants that reject terms and conditions should still be able to attempt to complete that quesitonnaire, they will again be asked to accept the privacy policy before starting the questionnaire, and will not be able to unless the privacy policy is accepted
| Not Started | As a member of staff, I need to ensure that participants have agreed to the UoD Ethics before they start the questionnaire, so that we don't violate the user privacy | - Revoke access to the questionnaire if the policy is rejected |  | 2 |  |  | - Before a user starts a questionnaire, they need to agree to a privacy policy. If the user rejects the privacy policy agreement, they cannot continue.
| Not Started |  | - option to change response if the questionnaire has not yet been completed |  |  |  |  | - Participants that reject terms and conditions should still be able to attempt to complete that quesitonnaire, they will again be asked to accept the privacy policy before starting the questionnaire, and will not be able to unless the privacy policy is accepted
| Not Started | As a participant. I want the ability to check the T&Cs and UOD Ethics before participating in the questionnaire so that I know information about myself is being used correctly | - Revoke access to the questionnaire if the policy is rejected |  | 2 |  |  | - Before a user starts a questionnaire, they need to agree to a privacy policy. If the user rejects the privacy policy agreement, they cannot continue.
| Not Started |  | - option to change response if the questionnaire has not yet been completed |  |  |  |  | - Participants that reject terms and conditions should still be able to attempt to complete that quesitonnaire, they will again be asked to accept the privacy policy before starting the questionnaire, and will not be able to unless the privacy policy is accepted

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.