## Agile Product Backlog
SPRINT BACKLOG
SPRINT # | User Story | Tasks | ASSIGNED TO | STORY POINTS | START DATE | STATUS | Date completed | Definition of Done | Velocity 1 | Velocity 2
Sprint 1 |  |  |  | 140
| As a member of staff, I want to be able to create questionnaires via the system, so that I don’t need to use external systems | Design and create database (questionnaire: title, questions, answers): - Create ER diagram - Normalise - Create database - Add data | Craig and Wei | 55 | 26/01/2021 | In Progress |  | -The website should look professional and the design should be approved by the stake holders -The website should have university branding -The text design should satifsy WCAG 2.0 AA | This section is for the drop-down list
|  | Design and create website: - Desgin pages (website template, create questionnaire page) - Create pages (website template, create questionnaire page) | Elliot, Alban, Zihan and Tianpeng |  | 26/01/2021 | In Progress |  | -The created questionaire should be saved in a database -The database should at least satisfy 3NF | Yes | High | Complete
|  | Java script and php, questionaire logic: - Connect to the database - Create a new questionnaire - Add questions | (Jonas & Tony) Elliot, Alban, Zihan and Tianpeng |  |  | Not Started |  | -The website has an ability to create and store a questionaire -The creator should be easy and intuitive to use approved by the stake holders -The website should be able to send the questionaire to be stored in the database
| As a user of the program, I want to be able to login so that I can access my information easily | Design and add to database (login: username, real name, password, role, access rights): - Add to ER diagram - Normalise - Add to database - Add data | Craig and Wei | 55 |  | In Progress |  | -The database should at least satisfy 3NF -The database should be able to store users and all needed data -Data about the users are name, role and permissions at the least
|  | Design and create pages: - login page - dashboard | Elliot, Alban, Zihan and Tianpeng |  |  | In Progress |  | -The website should look professional and the design should be approved by the stake holders -The website should have university branding -The text design should satifsy WCAG 2.0 AA
|  | Java script and php, questionaire logic: - Check login details against stored data, return appropriate result | (Jonas & Tony) Elliot and Alban |  |  | Not Started |  | -The website should be locked and redirect to login page If the user is not looged in -The user should be able to login and access info saved on the site -When the user is logged in they should be able to see their name and role
| As a member of staff, I need to ensure that participants have agreed to our privacy policy before they start the questionnaire, so the participant understand how are were going to use their data and that we don't violate the Data protection act and GDPR | Research, design and create page: - Collect privacy policy - design page - create page | Elliot, Alban, Zihan and Tianpeng | 2 |  | Not Started |  | -The website should post our privacy policy before participants can access any questionaires -The participant have to accept it before they can go futher into the website
|  | Add to database: - user accepted/rejected | Craig and Wei |  |  | Not Started |  | - Users can accespt or reject terms and conditions - response is correctly stored in the database
|  | Add accept/reject functionality | (Jonas & Tony) Elliot and Alban |  |  | Not Started |  | - When a user has accepted, they will be able to continue as a participant - When a user rejects terms and conditions, they are removed from that experiment
| As a member of staff, I need to ensure that participants have agreed to the UoD Ethics before they start the questionnaire, so that we don't violate the user privacy | Research, design and create page: - Collect privacy policy - design page - create page | Elliot, Alban, Zihan and Tianpeng | 2 |  | Not Started |  | -The website should post our UoD Ethics before participants can access any questionaires -The participant have to accept it before they can go futher into the website
|  | Add to database: - user accepted/rejected | Craig and Wei |  |  | Not Started |  | - Users can accespt or reject terms and conditions - response is correctly stored in the database
|  | Add accept/reject functionality | (Jonas & Tony) Elliot and Alban |  |  | Not Started |  | - When a user has accepted, they will be able to continue as a participant - When a user rejects terms and conditions, they are removed from that experiment
| As a participant. I want the ability to check the T&Cs before participating in the questionnaire so that I know information about myself is being used correctly | Research, design and create page: - Collect privacy policy - design page - create page | Elliot, Alban, Zihan and Tianpeng | 3 |  | Not Started |  | -The website should post our T&Cs before participants can access any questionaires -The participant have to accept it before they can go futher into the website
|  | Add to database: - user accepted/rejected | Craig and Wei |  |  | Not Started |  | - Users can accespt or reject terms and conditions - response is correctly stored in the database
|  | Add accept/reject functionality | (Jonas & Tony) Elliot and Alban |  |  | Not Started |  | - When a user has accepted, they will be able to continue as a participant - When a user rejects terms and conditions, they are removed from that experiment
| As a lab manager, I want to be able to create accounts so that new people can access the system | Create a stored procedure for adding a new user to the database | Craig and Wei | 13 |  | Not Started |  | - A stored procedure is available that creates a new user entry in the database with all the relevant information
|  | Design and create page: - lab manager, create new user | Elliot, Alban and Tianpeng |  |  | Not Started |  | -The website should look professional and the design should be approved by the stake holders -The website should have university branding -The text design should satifsy WCAG 2.0 AA -There should be a form where lab managers can add new users and enter all their data | No | Medium | In Progress
|  | Java script and php, questionaire logic: link database and html login functionality | (Jonas & Tony) Elliot and Alban |  |  | Not Started |  | -When a lab manager adds a new user they are created in the database correctly
| As a member of staff, I want questionnaires to have options for text answers, so that I can gauge responses accurately | Design and add to database: - store text answers, user ID | Craig and Wei | 5 |  | Not Started |  | -The database should at least satisfy 3NF -The database should be able to store users and all needed data -The database should be able to store Text type answers
|  | Design and create: - text input option when creating a questionnaire - participant questionnaire answer page | Elliot, Alban and Tianpeng |  |  | Not Started |  | -The website should look professional and the design should be approved by the stake holders -The website should have university branding -The text design should satifsy WCAG 2.0 AA -in the create questionaire sthere should be an qption to make text type questions
|  | Java script and php, questionaire logic: send questionnaire results to be stored in the database | (Jonas & Tony) Elliot and Alban |  |  | Not Started |  | It should be possible for the text type question to be saved in the database
| As a member of staff, I want questionnaires to have options for multiple choice answers, so that I can gauge responses accurately | Design and add to database: - store multiple choice answers, user ID | Craig and Wei | 5 |  | Not Started |  | -The database should at least satisfy 3NF -The database should be able to store users and all needed data -The database should be able to store multiple choice answers
|  | Design and create: - multiple choice input option when creating a questionnaire | Elliot, Alban and Tianpeng |  |  | Not Started |  | -The website should look professional and the design should be approved by the stake holders -The website should have university branding -The text design should satifsy WCAG 2.0 AA -In the create Questionaire page there should be a multiple choice ype question
|  | Java script and php, questionaire logic: send questionnaire results to be stored in the database | (Jonas & Tony) Elliot and Alban |  |  | Not Started |  | -It should be possible for the multiple choice question to be saved in the database
Sprint 2 |  |  | Allocated story points | 140 | [5 empty] | Low | Not Started

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.